## January 2013
Activity Code | Activity | Time Sheet for th month of January
P01 | Reading past research work. | Project Name | T2013
P02 | Requirements Analysis and understanding | Team Members: | Alpna
P03 | BackGround work for Project (Includes Student Profiles System) |  | Kumari Suhani
P04 | Documentation(includes usecases, Interaction Stories, test transactions, Flow of events, Screen navigation diagrams,other project documentation) |  | Priyasmita Ghosh
Meetings | Includes formal meetings with TA's, Professor and informal meetings among team. |  | Ruchika Sharma
Sai Naga Sravani Peraka
Satya Deepthi Bhagi
Sruti Davis
|  | Roll No. | Name | Activity Code | 2012-01-01 | 2012-01-02 | 2012-01-03 | 2012-01-04 | 2012-01-05 | 2012-01-06 | 2012-01-07 | 2012-01-08 | 2012-01-09 | 2012-01-10 | 2012-01-11 | 2012-01-12 | 2012-01-13 | 2012-01-14 | 2012-01-15 | 2012-01-16 | 2012-01-17 | 2012-01-18 | 2012-01-19 | 2012-01-20 | 2012-01-21 | 2012-01-22 | 2012-01-23 | 2012-01-24 | 2012-01-25 | 2012-01-26 | 2012-01-27 | 2012-01-28 | 2012-01-29 | 2012-01-30 | 2012-01-31
|  | MT2012013 | Alpna | P01 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | MT2012013 | Alpna | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4 | 3 | 2
|  | MT2012013 | Alpna | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P01 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 7 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 0 | OFF | 1.5 | 1 | 0 | 0 | 0 | 1.5 | 1
|  | MT2012069 | Kumari Suhani | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P01 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4 | 3 | 2
|  | MT2012105 | Priyasmita Ghosh | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P01 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 8 | OFF | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | OFF | 1:30 | 0 | 0 | 2 | 0 | 0.5 | 0 | 0 | 0 | 1:10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012119 | Ruchika Sharma | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P01 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4 | 3 | 2
|  | MT2012122 | Sai Naga Sravani Peraka | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P01 | 0 | 0 | 0 | 1 | 2 | 0 | 1 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 3 | 3 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 4 | 3 | 2
|  | MT2012129 | Satya Deepthi Bhagi | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 2
|  | MT2012140 | Sruti Davis | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## February 2013
Activity Code | Activity | Time Sheet for th month of February
P01 | Reading past research work. | Project Name | T2013
P02 | Requirements Analysis and understanding | Team Members: | Alpna
P03 | BackGround work for Project (Includes Student Profiles System) |  | Kumari Suhani
P04 | SRS Documentation(includes usecases, Interaction Stories, test transactions, Flow of events, Screen navigation diagrams,other project documentation) |  | Priyasmita Ghosh
P05 | Designing of Database and User interface |  | Ruchika Sharma
P06 | Coding and Unit Testing. |  | Sai Naga Sravani Peraka
P07 | Documentation for user manuals and guides |  | Satya Deepthi Bhagi
P08 | System Testing. |  | Sruti Davis
P09 | Review.
P10 | Bug Fixing and Re-testing.
Meetings | Includes formal meetings with TA's, Professor and informal meetings among team.
|  | Roll No. | Name | Activity Code | 01-02-2012 | 2012-02-02 | 2012-02-03 | 2012-02-04 | 2012-02-05 | 2012-02-06 | 2012-02-07 | 2012-02-08 | 2012-02-09 | 2012-02-10 | 2012-02-11 | 2012-02-12 | 2012-02-13 | 2012-02-14 | 2012-02-15 | 2012-02-16 | 2012-02-17 | 2012-02-18 | 2012-02-19 | 2012-02-20 | 2012-02-21 | 2012-02-22 | 2012-02-23 | 2012-02-24 | 2012-02-25 | 2012-02-26 | 2012-02-27 | 2012-02-28
|  | MT2012013 | Alpna | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 2 | 8 | 8 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P05 | 2 | 2012-02-02: 0; 2012-02-03: 0; 2012-02-04: 0; 2012-02-05: 0; 2012-02-06: 0; 2012-02-07: 0; 2012-02-08: 0; 2012-02-09: 0
|  | MT2012013 | Alpna | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 1 | 0 | 1:30 | 0 | 0 | 2 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 2 | 10 | 6 | 7 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P05 | 2 | 2012-02-02: 0; 2012-02-03: 0; 2012-02-04: 0; 2012-02-05: 0; 2012-02-06: 0; 2012-02-07: 0; 2012-02-08: 0
|  | MT2012069 | Kumari Suhani | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 1 | 1 | 0 | 3 | 0 | OFF | 1.5 | 1 | 0 | 0 | 0 | 1.5 | 1
|  | MT2012105 | Priyasmita Ghosh | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 2 | 8 | 8 |  |  | 2 | 1 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | MT2012105 | Priyasmita Ghosh | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 2 | 0 | 0 | 1 |  | 1 | 2 | 3 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0
|  | MT2012105 | Priyasmita Ghosh | Meetings | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1:30 | 0 | 0 | 2 |  | 0.5 | 0 | 0 | 0 | 1:10 |  | 0 | 0 | 0 | 0 |  | 0
|  | MT2012119 | Ruchika Sharma | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012119 | Ruchika Sharma | P03 | 1.5 | 0 | 5 | 1 | 2 | 0 | 7 | 2 | 2 | 6 | OFF | 0 | 2 | 0 | 0 | 0 | 0 | OFF | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012119 | Ruchika Sharma | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | OFF | 2 | 0 | 3 | 3 | 2 | 1 | OFF | 2 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012119 | Ruchika Sharma | Meetings | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 1 | 1 | OFF | 1.3 | 0 | 1.4 | 2 | 0 | 0.5 | OFF | 2 | OFF | 1.5 | 1 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012122 | Sai Naga Sravani Peraka | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | LEAVE | LEAVE | LEAVE | LEAVE | LEAVE | 0 | 0 | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012122 | Sai Naga Sravani Peraka | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 2 | 8 | 8 | OFF | LEAVE | LEAVE | LEAVE | LEAVE | LEAVE | 0 | 0 | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012122 | Sai Naga Sravani Peraka | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | OFF | LEAVE | LEAVE | LEAVE | LEAVE | LEAVE | 7 | 2 | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012122 | Sai Naga Sravani Peraka | P05 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | LEAVE | LEAVE | LEAVE | LEAVE | LEAVE | 0 | 0 | 0 | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012122 | Sai Naga Sravani Peraka | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 1 | OFF | LEAVE | LEAVE | LEAVE | LEAVE | LEAVE | 0.5 | 0 | 2 | OFF | 1.5 | 1 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012129 | Satya Deepthi Bhagi | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 0.5 | 9 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 2 | 0.5 | 0 | 5 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P05 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.25 | 1 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | OFF | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012140 | Sruti Davis | P03 | 0 | 3 | 1.5 | 3 | 3 | 6 | 0 | 10 | 6 | 7 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | OFF | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012140 | Sruti Davis | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 1 | 2 | 7 | 7 | 3 | OFF | OFF | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012140 | Sruti Davis | P05 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | OFF | 0 | OFF | OFF | OFF | OFF | OFF | OFF
|  | MT2012140 | Sruti Davis | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 3 | 0 | OFF | 1.5 | 1 | 0.5 | 0 | 1 | OFF | OFF | 2 | OFF | OFF | OFF | OFF | OFF | OFF

## March 2013
Activity Code | Activity | Time Sheet for th month of March
P01 | Reading past research work. | Project Name | T2013
P02 | Requirements Analysis and understanding | Team Members: | Alpna
P03 | BackGround work for Project (Includes Student Profiles System) |  | Kumari Suhani
P04 | SRS Documentation(includes usecases, Interaction Stories, test transactions, Flow of events, Screen navigation diagrams,other project documentation) |  | Priyasmita Ghosh
P05 | Designing of Database and User interface |  | Ruchika Sharma
P06 | Coding and Unit Testing. |  | Sai Naga Sravani Peraka
P07 | Documentation for user manuals and guides |  | Satya Deepthi Bhagi
P08 | System Testing. |  | Sruti Davis
P09 | Review.
P10 | Bug Fixing and Re-testing.
Meetings | Includes formal meetings with TA's, Professor and informal meetings among team.
|  | Roll No. | Name | Activity Code | 2012-03-01 | 2012-03-02 | 2012-03-03 | 2012-03-04 | 2012-03-05 | 2012-03-06 | 2012-03-07 | 2012-03-08 | 2012-03-09 | 2012-03-10 | 2012-03-11 | 2012-03-12 | 2012-03-13 | 2012-03-14 | 2012-03-15 | 2012-03-16 | 2012-03-17 | 2012-03-18 | 2012-03-19 | 2012-03-20 | 2012-03-21 | 2012-03-22 | 2012-03-23 | 2012-03-24 | 2012-03-25 | 2012-03-26 | 2012-03-27 | 2012-03-28 | 2012-03-29 | 2012-03-30 | 2012-03-31
|  | MT2012013 | Alpna | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P04 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3
|  | MT2012013 | Alpna | Meetings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | MT2012069 | Kumari Suhani | P02 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P03 | OFF | OFF | OFF | OFF | 1 | 1 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P04 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P05 | OFF | OFF | OFF | OFF | 1 | 1 | OFF | OFF | OFF | OFF | OFF | OFF | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P06 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | Meetings | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P02 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P03 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P04 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0
|  | MT2012105 | Priyasmita Ghosh | P05 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P06 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | Meetings | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P02 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  | MT2012119 | Ruchika Sharma | P03 | OFF | OFF | OFF | OFF | 1 | 1 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 1 | 4 | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P04 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P05 | OFF | OFF | OFF | OFF | 1 | 1 | OFF | OFF | OFF | OFF | OFF | OFF | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P06 | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 7 | 8 | 1 | 0 | 0 | 0 | 2 | 4 | 3
|  | MT2012119 | Ruchika Sharma | Meetings | OFF | OFF | OFF | OFF | 0 | 0 | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P02 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P03 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P04 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P05 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P06 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 2 | 5 | 4 | 0 | 5 | 5 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3
|  | MT2012122 | Sai Naga Sravani Peraka | Meetings | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | MT2012129 | Satya Deepthi Bhagi | P02 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P03 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P04 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P05 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P06 | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 4 | 4 | 5 | 0 | 4 | 5 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3
|  | MT2012129 | Satya Deepthi Bhagi | Meetings | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | OFF | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | MT2012140 | Sruti Davis | P02 | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P03 | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P04 | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P05 | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P06 | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1
|  | MT2012140 | Sruti Davis | Meetings | OFF | OFF | OFF | OFF | OFF | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## April 2013
Activity Code | Activity | Time Sheet for th month of April
P01 | Reading past research work. | Project Name | T2013
P02 | Requirements Analysis and understanding | Team Members: | Alpna
P03 | BackGround work for Project (Includes Student Profiles System) |  | Kumari Suhani
P04 | SRS Documentation(includes usecases, Interaction Stories, test transactions, Flow of events, Screen navigation diagrams,other project documentation) |  | Priyasmita Ghosh
P05 | Designing of Database and User interface |  | Ruchika Sharma
P06 | Coding and Unit Testing. |  | Sai Naga Sravani Peraka
P07 | Documentation for user manuals and guides |  | Satya Deepthi Bhagi
P08 | System Testing. |  | Sruti Davis
P09 | Review.
P10 | Bug Fixing and Re-testing.
Meetings | Includes formal meetings with TA's, Professor and informal meetings among team.
|  | Roll No. | Name | Activity Code | 2012-04-01 | 2012-04-02 | 2012-04-03 | 2012-04-04 | 2012-04-05 | 2012-04-06 | 2012-04-07 | 2012-04-08 | 2012-04-09 | 2012-04-10 | 2012-04-11 | 2012-04-12 | 2012-04-13 | 2012-04-14 | 2012-04-15 | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-21 | 2012-04-22 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-28 | 2012-04-29 | 2012-04-30
|  | MT2012013 | Alpna | P02 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P06 | 3 | 3 | 6 | 3 | 3 | 4 | 4 | 4 | 2 | 2 | 3 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | P07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012013 | Alpna | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 2 | 2 | 1 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
|  | MT2012069 | Kumari Suhani | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | P06 | 3 | 3 | 6 | 3 | 3 | 4 | 4 | 4 | 4 | 2 | 3 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0
|  | MT2012069 | Kumari Suhani | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P02 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P06 | 0 | 4 | 4 | 3 | 2 | 3 | 3 | 5 | 3 | 0 | 3 | 5 | 4 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | P07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012105 | Priyasmita Ghosh | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P10 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | OFF | 0 | 8 | 0 | 0 | 0 | 0 | OFF | OFF | 6 | OFF | 1 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P04 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | OFF | OFF | 0 | OFF | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P05 | OFF | 0 | 0 | 0 | 0 | 0 | OFF | 0 | 0 | 0 | OFF | 0 | 0 | 0 | 0 | 0 | 0 | OFF | OFF | 0 | OFF | 0 | 0 | 0 | 0
|  | MT2012119 | Ruchika Sharma | P06 | OFF | 3 | 4 | 2 | 1 | 1 | OFF | 5 | 4 | 2 | OFF | 4 | 1 | 7 | 4 | 3 | 4 | OFF | OFF | 1 | OFF | 0 | 6 | 4 | 6
|  | MT2012119 | Ruchika Sharma | Meetings | OFF | 0 | 0 | 0.1 | 0 | 0 | OFF | 0 | 0 | 0.1 | OFF | 0 | 0 | 1 | 0 | 4 | 0 | OFF | OFF | 0 | OFF | 0 | 0 | 2 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P06 | 3 | 3 | 6 | 3 | 2 | 3 | 4 | 4 | 2 | 2 | 0 | 2 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | P07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012122 | Sai Naga Sravani Peraka | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P06 | 3 | 3 | 6 | 3 | 2 | 3 | 4 | 4 | 2 | 2 | 0 | 2 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | P07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012129 | Satya Deepthi Bhagi | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P06 | 3 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 4 | 4 | 5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | P07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
|  | MT2012140 | Sruti Davis | Meetings | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0